PROJECT BRIEFER

| Project Title | OUTSCALING OF OFF-SEASON ONION PRODUCTION IN THE RICE-BASED AREAS IN NUEVA VIZCAYA |
| --- | --- |
| Implementing Agency | Department of Agriculture – Regional Field Office No. 2 |
| Project Leader | Ms. Chonalyn A. Pascua |
| Project Duration | July 1, 2020 to June 30, 2022 |
| Approved Fund | PhP 5,000,000.00 |
| General Objectives | To ensure sustainable production and availability of off-season onion through mature and sustainable technologies utilization in Region 2 |
| Specific Objectives | - To increase production of off-season onion from 0.50 kg/sqm (Station Trial) to 1.04 kg/sqm (CPAR trial) through matured packaged of technologies (POT) - To strengthen capacities of 125 farmers and 3 municipalities on production/post-production and other relevant technologies; and - To develop sustainable support mechanism and linkages with various support services. |
| Technology Developed |  |
| Technology Description | Planting Super Pinoy variety for off-season onion production in August and December-January with the provision of rain shelter to avoid excessive moisture and following best cultural management such as raised beds, solarization, nutrient and pest management |
| Expected Output 1 | - Increased production of onion from 0.50 kg/sqm to 1.04 kg/sqm - Established 2.5 ha as demonstration farms |
| Actual Accomplishments | - Harvested an average of 1.19 kg/sqm (equivalent to 11.19 mt/ha) of onion per farmer cooperator sold at P100-250/kg - Result of partial Cost and Return Analysis revealed the following information: - Net income: Php 35,700.00 - ROI: 199% - Note: Partial results coming from 4 FCs since data collection is still ongoing - Established 132 model farms with at least 200 sqm per farmer - Transferred technology to 2 FCAs |
| Expected Output 2 | - Capacitated 125 farmers & 3 farmers’ association - Aritao: 90 farmers - Bagabag: 20 farmers - Dupax del Sur: 15 farmers - Conducted 6 batches of trainings - Developed 1 IEC material & distributed 500 copies |
| Actual Accomplishments | - Conducted 4 batches of trainings on POT on Off-Season Onion Production & basic record-keeping with 132 farmers - Conducted 3 field days with a total of 240 participants - Distributed customized IEC materials |
| Expected Output 3 | Linked 3 organizations to various institutions & linked to market outlets |
| Actual Accomplishments | - Transferred off-season onion production technologies to FAFOGA in Aritao, Nueva Vizcaya & Bagabag High Value Crops Producers Association in Bagabag, Nueva Vizcaya - Transferred the technology to FOD-HVC for their expansion |
| Technology Description | Planting Super Pinoy variety for off-season onion production in August and December-January with the provision of rain shelter to avoid excessive moisture and following best cultural management such as raised beds, solarization, nutrient and pest management |
| Potential Impact | Utilizing the off-season onion production technologies will lead to increased supply of onion and increased income of onion farmers |
| Beneficiaries/Users/ Adopters | - 132 farmers in Aritao and Bagabag, Nueva Vizcaya trained on POT on Off-Season Onion Production & basic record-keeping with 200 sqm-model farm established per farmer - 240 participants of field days conducted - 2 FCs (FAFOGA & Bagabag High Value Crops Producers Association) as adopter of the technology |
| Summary of Findings |  |
| Conclusion |  |
| Recommendation |  |
| Sustainability Plan |  |